## Slide 1: Engineering Management
Lecture 37,38,39
Project Organization,
Leadership, and Control

## Slide 2: Objectives:
Explain how the project is managed in the different organization structures.
Describe some of the characteristics of an effective project manager.
Describe the different types of project contracts.

## Slide 3: Organization structure and project success
Functional organization. The project is divided into segments and assigned to relevant functional areas and/or groups within functional areas. The project is coordinated by functional and upper levels of management.
Functional matrix. A person is formally designated to oversee the project across different functional areas. This person has limited authority over functional people involved and serves primarily to plan and coordinate the project. The functional managers retain primary responsibility for their specific segments of the project.
Balanced matrix. A person is assigned to oversee the project and interacts on an equal basis with functional managers. This person and the functional managers jointly direct workflow segments and approve technical and operational decisions.
Project matrix. A manager is assigned to oversee the project and is responsible for the completion of the project. The functional manager’s involvement is limited to assigning personnel as needed and providing advisory expertise.
Project team. A manager is put in charge of a project team composed of a core group of personnel from several functional areas and/or groups, assigned on a full-time basis. The functional managers have no formal involvement.

## Slide 4: The project manager
Characteristics of effective Project Managers
Technical Skills
Administrative Skills
Interpersonal skill

## Slide 5: Developing Project Management skills
The Manager’s charter
Specification of project priority relative to other activities
Designation as the primary contact with the customer
Authority to define the work to be performed by supporting departments in terms of cost, schedule, and performance
Control over the project budget, with signature authority on all work authorizations
Responsibility to schedule and hold design reviews, determine the agenda and representa-tion, and establish responsibility for follow-up action
Responsibility for configuration and change control and for approving changes
Authority to constitute and chair the make-or-buy and source selection board
Responsibility for regular reporting to general management of project status and identification of any factors inhibiting project success
Participation in the merit review process for all personnel on loan to the project

## Slide 6: Types of contracts
Fixed-Price contract
Firm fixed-price contracts require the contractor to provide an agreed product and/or service for a specified price. The contractor realizes the total profit or loss and thus has maximum motivation to eliminate waste. The buyer must assure that the specifications define clearly what has been purchased for the fixed price.
Fixed-price with escalation contracts are firm fixed-price, except that the contractor’s price can be adjusted to incorporate any increases in specified labor and material rates. This is especially useful in construction work where industry-wide union wage rates are scheduled for renegotiation during the life of the contract.

## Slide 7: Types of contracts
Fixed-Price contract
Fixed-price, redeterminable contracts can be adjusted later to reflect actual costs. The contractor therefore has less motivation to keep costs to a minimum before that adjustment is made.
Fixed-price incentive contracts provide that the contractor and buyer share savings within a certain range, but establish a maximum cost for the buyer above which the contractor bears the total risk.

## Slide 8: Types of contracts
Cost type contract
Cost plus incentive fee contracts establish an estimated target cost and target fee (profit). Within a specified range about the target, contractor and buyer share added costs or savings in an agreed ratio, but outside that range the buyer bears the total risk.
Cost plus fixed-fee contracts require the buyer to pay all costs, plus an agreed-upon fee.
Time and materials contracts are common in repair, maintenance, and emergency situations, and they involve payment at agreed-upon rates (high enough to include profit) for hours worked, plus reimbursement of invoices for actual materials used.